## Sheet1
Resource Name: | Hussain Bootwala
Dubai Police Staff _ Attendance & Task Sheet
Period: | 01 - 30 Apr 2016
Name | Date | Clock In | Clock Out | Work Time | Absent (Y/N) | Task Description
Hussain Bootwala | 2016-04-01 | Day-off
Hussain Bootwala | 4/2/2016 | Day-off
Hussain Bootwala | 4/3/2016 | 7:30 | 16:45 | 9:15 | N | Due to non availability of System I was working with saddam of website project and went through the complete website for frontend framework.
Hussain Bootwala | 4/4/2016 | 7:30 | 16:30 | 9:00 | N | Started with Map interactive section on website homepage. Completed with map filter through JS and designed filter part frontend as per the psd provided by Sami
Hussain Bootwala | 4/5/2016 | 7:30 | 17:10 | 9:40 | N | Completed with map html and matched with the given psd. Interactivity for location and route defining filter added. Animation on map like google maps done
Hussain Bootwala | 4/6/2016 | 7:30 | 16:30 | 9:00 | N | Completed with map frontEnd functionality and also completed the social tabs as per the psd
Hussain Bootwala | 4/7/2016 | 7:27 | 16:30 | 9:03 | N | 1. Completed with map and social tabs testing. 2. Inserted Live feeds for all the social tabs
Hussain Bootwala | 4/8/2016 | Day-off
Hussain Bootwala | 4/9/2016 | Day-off
Hussain Bootwala | 4/10/2016 | 7:30 | 17:10 | 9:40 | N | Worked on additional points for google maps for geolocation. Additional design tweaks for animation and effects
Hussain Bootwala | 4/11/2016 | 7:40 | 16:30 | 8:50 | N | Completed with all the points on maps as given by Sami. Started with Footer design front end
Hussain Bootwala | 4/12/2016 | 7:27 | 16:50 | 9:23 | N | completed with footer html matching the psd. Also worked on basic animations for initial user experience
Hussain Bootwala | 4/13/2016 | 7:35 | 17:15 | 9:40 | N | Worked on animation part in footer and responsive testing for tablet and mobile version
Hussain Bootwala | 4/14/2016 | 7:40 | 16:45 | 9:05 | N | Worked on responsive changes as per new UX required in mobile View. Icons changed as per psd.
Hussain Bootwala | 4/15/2016 | Day-off
Hussain Bootwala | 4/16/2016 | Day-off
Hussain Bootwala | 4/17/2016 | 7:35 | 16:45 | 9:10 | N | Worked on footer animation change. Solved the Jquery issue on adding comma rolling animation numbers. Changed hover effects on buttons. done with responsive popups as example given my Sami
Hussain Bootwala | 4/18/2016 | 7:50 | 16:55 | 9:05 | N | Completed with Footer work with responsive testing and animations as required. Completed OSS widget work with compatibility on IE8
Hussain Bootwala | 4/19/2016 | 7:30 | 16:55 | 9:25 | N | Started with Streamline design PSD. Completed Google cards hover effect. Worked on Under Maintenance Popup html
Hussain Bootwala | 4/20/2016 | 7:35 | 17:15 | 9:40 | N | Worked on Streamline Events section , Document step wise form section
Hussain Bootwala | 4/21/2016 | 7:20 | 18:00 | 10:40 | N | Completed with Document search step wise form section according to psd. Started with results popup animation
Hussain Bootwala | 4/22/2016 | Day-off
Hussain Bootwala | 4/23/2016 | Day-off
Hussain Bootwala | 4/24/2016 | 7:30 | 16:55 | 9:25 | N | Worked on Filter for steamline. 3d flip animation for popups done. Completed with Share Dropdown as per the refrence provided
Hussain Bootwala | 4/25/2016 | 7:30 | 17:25 | 9:55 | N | completed with filter functionality with scrolling content. fixed SVG images for multicolor icons. Fixed box hover effect like google
Hussain Bootwala | 4/26/2016 | 7:30 | 18:15 | 10:45 | N | Changed filter and scrolling streams content as per changed requirement and added additional effects in its showcase. started with enquiry form validations
Hussain Bootwala | 4/27/2016 | 7:30 | 17:15 | 9:45 | N | Completed with steps form Validation. solved drop shadow fading out with jQuery.
Hussain Bootwala | 4/28/2016 | 7:45 | 16:30 | 8:45 | N | changed main carousel for filter as per the requirement and working on to update the carousel with animation as asked. Done with Js functionality on filter and carousel
Hussain Bootwala | 4/29/2016 | Day-off
Hussain Bootwala | 4/30/2016 | Day-off